## Risk Register
Risk Register
This document is maintained to manage all risks identified for the Smart Home Analytics project (Project A: Energy Profiling & Customer Benchmarking)
# | Issue | Risk Description | Date Added | Review Date | Accountable Staff | Likelihood | Consequence | Risk Rating | Treatment / Controls | Status | Status Comment
1 | Segmentation not defensible | There is a risk that we cannot show reliable groups of similar homes, as the brief requires, because our three methods found no clear groups in the data and the data appears to be computer-generated, not real. | 2026-10-25 | 2026-10-30 |  | Likely | Major | High | Report the finding openly; use each home's percentile rank per appliance as the main comparison; present any groups as a labelled descriptive layer; confirm the approach with the mentor. | Treatment in progress | All three models gave scores far below 0.25 and none was clearly better than shuffled data. The mentor supported percentile rank as the main comparison. Use of a descriptive 3-group layer is still to be confirmed.
2 | Segments over-claimed to clients | There is a risk that clients are given advice based on differences between homes that are only chance, because groupings and rankings could be read as real household behaviour in the dashboard and the 50-unit sample report. | 2026-10-25 | 2026-10-30 |  | Possible | Major | High | State limitations on every segment and ranking view; word findings as comparisons, not behaviour or savings; keep recommendations to the appliance-level pattern the data support; mentor reviews outputs before the client demo. | Treatment planned | Percentile rank and nearest-neighbour peers are planned as the main comparison. Wording and limitation notes will be added when dashboard version 1 is finalised.
3 | Unstable percentile ranks | There is a risk that a home's percentile rank per appliance is misread as a stable habit, because each rank rests on about 20 readings and the rank changes when a different half of the readings is used. | 2026-10-25 | 2026-10-30 |  | Likely | Moderate | High | Show the number of readings behind each rank; show broad bands (below 25th, 25th to 75th, above 75th) beside the exact figure; label ranks as position in this dataset only. | Treatment planned | A split-half check on the real data showed ranks do not repeat (correlation about zero for every appliance). Bands and reading counts are to be added to the household profile page.
4 | Dashboard scope against available time | There is a risk that planned dashboard pages are not finished before the Week 6 presentation, because intern capacity is part-time and several pages (peers, bands, time-of-day, temperature, drill-through) remain to be built. | 2026-10-25 | 2026-10-30 |  | Likely | Moderate | High | Prioritise the core pages (overview, household profile, peer comparison); treat time-of-day, temperature and cost views as optional; agree the milestone plan with the mentor each week; cut scope early if behind. | Treatment in progress | Dashboard version 1 covers the portfolio overview and household profile; the peer and segment page is a frame only. Remaining pages are being sequenced against the Week 5 and Week 6 dates.
| A senior team member is unavailable | [7 empty] | Have someone to be the second in charge
5 | Models compared on different set-ups | There is a risk that differences between model results are caused by set-up, not method, because the feature tables, the number of shuffled tests and the stability tests have differed between models. | 2026-10-25 | 2026-11-06 | Khanh, Intern - Gaussian Mixture modelling | Possible | Moderate | Medium | Use one shared feature table (mean kWh per reading by appliance); use the same number of shuffled copies (100 or more) and the same stability test and p-value method for all three models; record the settings used. | Treatment in progress | The Gaussian Mixture notebook now uses the shared 10-column table. The script, the number of shuffles (20 so far) and the stability test still need to be aligned. A 100-shuffle check gave the same conclusion.
6 | Power BI licence for sharing | There is a risk that the stakeholder cannot view the dashboard online, because sharing a report in Power BI Service needs a paid licence and none has been confirmed for the team. | 2026-10-25 | 2026-11-06 | Tung Nguyen, Mentor | Possible | Moderate | Medium | Ask the mentor to provide licences or approve the 60-day free trial; fall back to presenting from Power BI Desktop, or share a .pbix file and a PDF export; confirm what the stakeholder needs to view the dashboard. | Under assessment | Team members can sign in to Power BI Service but cannot share reports. The licence question has been added to the mentor meeting agenda.
7 | Week 5 stakeholder test not arranged | There is a risk that the tool is not tested with a consulting-team stakeholder before the final presentation, because the stakeholder, availability and session format have not been confirmed. | 2026-10-25 | 2026-11-06 |  | Possible | Moderate | Medium | Confirm the stakeholder, date and format with the mentor; prepare a Desktop demo and a PDF fallback; collect feedback in writing and record the changes made. | Identified | Stakeholder name, availability and session format are open items for the mentor.
8 | Key-person dependency | There is a risk that analysis or dashboard work stalls, because each model and each dashboard page is owned by one or two interns with limited weekly hours. | 2026-10-25 | 2026-11-06 |  | Possible | Moderate | Medium | Keep code and data tables in one shared team folder; pair on each model; record who owns what in the milestone plan; check progress at each weekly mentor review. | Treatment planned | Modelling is split across the team, with one model per intern or pair. The shared folder and ownership list are to be set up.
9 | Documentation and reuse on new data | There is a risk that another team member cannot rerun the analysis or adapt the tool to a new dataset, because notebooks and scripts differ and column names, file paths and settings are fixed in the code. | 2026-10-25 | 2026-11-06 | Khanh, Intern - Gaussian Mixture modelling | Possible | Moderate | Medium | Keep one documented script per model with settings at the top; use the same feature-building step; write a short README with run steps and expected outputs; test the tool on a second dataset with different column names. | Treatment in progress | A step-by-step notebook and a configurable script exist for the Gaussian Mixture model. The script and notebook still use different feature tables and need to be aligned.
10 | Undetected errors in analysis code | There is a risk that coding or logic errors go undetected and reach the mentor or client, because results have not been independently checked by a second team member. | 2026-10-25 | 2026-11-06 |  | Unlikely | Major | Medium | Peer review the key steps; reproduce each result with a second method or by hand; test the code on simulated data with known groups; record corrections in the project notes. | Treatment in progress | Code has been tested on simulated data with planted groups, and the Gaussian Mixture conclusions match K-means and Hierarchical. Formal peer review is still to be scheduled.
11 | Communicating a no-segments finding | There is a risk that the executive panel reads the finding as a failed project, because the weekly briefs and final presentation may not explain clearly why no clear household groups were found and what the tool still delivers. | 2026-10-25 | 2026-11-06 |  | Possible | Moderate | Medium | Lead each brief with the finding and its business meaning; show the percentile comparison as the working tool; state limits in plain language; rehearse the answer to 'are the segments real?' before each review. | Treatment planned | The mentor has been asked whether a descriptive 3-group layer with a stated limitation is acceptable.
12 | Brief and data do not match | There is a risk that examples in the brief cannot be produced, because the data show no seasonal or household-size effect and contain 10 appliance types where the brief states 9. | 2026-10-25 | 2026-11-06 |  | Likely | Minor | Medium | Tell the mentor early; describe archetypes only where the data support them (appliance type is the clear signal); record the 10 appliance types in the documentation. | Treatment planned | Checked on the data: season averages differ by about 0.02 kWh and household size changes within all 500 homes, so a winter-heavy example cannot be shown.
13 | Privacy of household data | There is a risk that household-level energy data could be disclosed, because the tool writes per-home files and may later be used on real client data. | 2026-10-25 | 2026-11-06 |  | Unlikely | Major | Medium | Use anonymised home IDs only; keep outputs in the shared team folder with restricted access; do not upload client data to external tools; confirm privacy requirements before any real client data is used. | Treatment planned | Current work uses the anonymised Kaggle dataset only; no client data has been used.
14 | Assumed prices read as findings | There is a risk that the optional cost scenario is read as a finding, because it would use assumed electricity prices by time of day, not a pattern found in the data. | 2026-10-25 | 2026-11-06 |  | Unlikely | Minor | Low | Label the page as an assumption and illustration; show the prices used; keep it separate from the segment and ranking pages; include it only if the mentor approves. | Under assessment | Whether to include the cost scenario has been added as a question for the mentor.

## Reference Lists
Status | Likelihood | Consequence | Risk Rating | Treatment Response | Status option | Suggested meaning
Identified | Rare | Insignificant | Low | Avoid | Identified | The risk has been recorded but assessment is not complete.
Under assessment | Unlikely | Minor | Medium | Reduce | Under assessment | Likelihood, consequence, controls or ownership are being assessed.
Treatment planned | Possible | Moderate | High | Transfer / share | Treatment planned | A treatment approach is agreed but implementation has not started.
Treatment in progress | Likely | Major | Extreme | Accept | Treatment in progress | Agreed controls or treatments are being implemented.
Monitoring | Almost certain | Severe |  |  | Monitoring | Controls are operating and the risk is being monitored through scheduled reviews.
Accepted |  |  |  |  | Accepted | The authorised decision-maker has accepted the residual risk.
Escalated |  |  |  |  | Escalated | The risk requires consideration at a higher level or is outside tolerance.
Closed |  |  |  |  | Closed | The risk no longer applies or has been reduced sufficiently and closure is approved.